## Read Me
Project Tracker — Employee Internal Transfer Digital Journey (SDD Assessment)
Source: docs/Requirement for SDD.docx §4 (Developer Assignment), §5 (Evaluation Criteria),
§6 (Recommended 10-Day Timeline), §7 (Milestones).
This workbook is the spreadsheet twin of TRACKER.md at the project root — same content,
laid out for convenient day-to-day updating with dropdown-validated Status/Coverage columns.
How to use it:
• Update Status / Coverage / Notes / Actual Date(s) cells as work happens.
• Status and Coverage cells are dropdowns — click a cell to see the arrow, pick a value,
don't free-type (keeps the sheet consistent and filterable).
• The 'Effort Log' sheet has ~150 pre-validated blank rows ready for new entries — just
fill in Date / Day # / Hours as you go; 'Running Total' updates itself automatically.
• This tracks the assessment's OWN structure (deliverables, evaluation weighting, the
10-day timeline, milestones) — it is NOT a replacement for .ai-context/status.md, which
tracks the SDD artefact chain's internal state (each feature's spec/plan/task status).
This workbook is the outer, assessment-facing view; status.md is the inner detail.
Sheet guide:
1. Deliverables — the 10 items from §4 (the source skips 'Deliverable 6' itself).
2. Evaluation Criteria — the weighted scoring table from §5, with a coverage self-check.
3. 10-Day Timeline — the Day 1–10 plan from §6, with Status/Actual Date/Notes to fill in.
4. Milestones — the 4 milestones from §7.
5. Effort Log — running hours log against the ~30–35 hr / 8-day expectation.
6. Next Actions — the immediate to-do list, in order.
Last updated: 2026-09-21 (all 63 tasks across all 9 specs implemented and Gate 2 Merged; remaining gap is the standalone Security Assessment document and the final walkthrough/demo)

## Deliverables
Deliverables Checklist (§4)
The source document's numbering skips from Deliverable 5 to Deliverable 7 — no 'Deliverable 6' exists in the original.
# | Deliverable | Status | Artefact(s) | Notes
1 | Requirement / Discovery Analysis | Done | .ai-context/BRD.md, .ai-context/discovery-analysis.md | 7 BRD entries; business-vs-technical decisions distinguished throughout; assumptions/dependencies/out-of-scope captured per entry.
2 | Feature Specification (.md) + Acceptance Criteria | Done | .ai-context/specs/*.spec.md (9 files) | Core spec is internal-transfer-workflow.spec.md; 6 original supporting specs (auth, users, org structure, app constants, audit trail, admin oversight) plus 2 UI-layer specs added once real implementation began (admin-panel-ui, stakeholder-panel-ui). Several specs gained amended/new ACs mid-implementation as real gaps surfaced, each flagged and re-reviewed at Gate 1, not silently applied.
3 | Spec-Derived Test Cases | Done | .ai-context/test_cases/*.test_cases.md (7 files) + _integration.md | QA-expanded for the original 7 specs. ~20 Open QA Questions surfaced. _integration.md regenerated: 10 cross-feature scenarios. Gap: the 2 later-added UI specs never got their own QA-expanded test_cases/ file — their Red tests were written from the spec's own UT table and real usage findings instead.
4 | Technical Plan | Done | .ai-context/plans/*.plan.md (9 files) | All 9 specs have a drafted plan; Constitution Check completed for each.
5 | Task Decomposition | Done | .ai-context/tasks/*.tasks.md (9 files) | All 9 specs decomposed and fully implemented — every task Merged: rbac-api-security (8), user-management-console (7), org-structure-management (3), application-constants-management (2), internal-transfer-workflow (13), transfer-audit-trail (4), transfer-admin-oversight (3), admin-panel-ui (10), stakeholder-panel-ui (13) — 63 tasks total, every AC covered, no Coverage Gaps. Task counts grew past the original decomposition as real implementation/usage surfaced genuine gaps, each a proper Red->Green->Gate2 task, never a silent patch.
6 | (no Deliverable 6 in source document) | N/A |  | Gap in the source numbering itself, not this tracker.
7 | AI Prompts | Done | prompts/*.md (7 workflow-level + 63 per-task) | The 7 reusable workflow prompt files plus 63 real per-task prompt files, one per task, each scoped with explicit do-not-touch sibling-task boundaries.
8 | Security Assessment | Not Started |  | Still no standalone security assessment document. Every one of the 63 Merged tasks' Gate 2 evidence includes its own Security Checklist pass, and one real production-severity gap was found and fixed mid-session (no live MongoDB connection outside tests — every real deployment would 500; fixed via rbac-api-security.T08) — but none of this is consolidated into the one reviewable document this deliverable asks for.
9 | Gate 1 Review | Done | .ai-context/gate-reviews/gate1-review-*.md (9 files, 3 with re-confirmation sections) | All 9 specs Approved (7 original + 2 UI-layer specs added during implementation). Plus 3 amended-AC re-confirmations mid-implementation, each a real spec-content change caught during real usage: internal-transfer-workflow.AC19, user-management-console.AC13, and a 4-AC/1-new-AC batch (AC13/AC14/AC18/AC22/new AC25). All Approved. Same reviewer-identity caveat as before.
10 | Gate 2 Evidence | Done | .ai-context/gate-reviews/gate2-evidence-*.md (9 files) | All 63 tasks across all 9 specs reviewed and Merged. Every task's AC verification, Security Checklist, and outcome recorded; no task ever self-marked Merged — every verdict is a transcribed human (Test Reviewer) decision. 638/638 tests passing project-wide, tsc/eslint/next build all clean.

## Evaluation Criteria
Evaluation Criteria (§5)
Weighted scoring table, with an honest self-check of current coverage.
Area | Weight | Current Coverage | Notes
Business journey understanding | 10% | Strong | BRD/discovery captures the journey end-to-end from the SOW, including cross-role handoffs (Manager -> HR -> Payroll/IT/Facilities -> HR).
Ambiguity & discovery | 15% | Strong | ~15 distinct open items logged in discovery-analysis.md across all 7 BRD entries; several resolved with explicit rationale as the chain progressed.
Specification quality | 20% | Strong | 9 specs, each with Intent/Context/API Contract/AC/Unit Test Cases/Out-of-Scope/NFRs; no invented ACs or payload shapes — every mid-implementation amendment re-confirmed at Gate 1, not silently applied.
Acceptance criteria & testability | 15% | Strong | Every AC individually IDed, given/when/then; e.g. internal-transfer-workflow alone now has 25 (grew from 19 as real gaps surfaced and were formally amended in). QA-expanded test cases add ~20 further scenarios per spec, for the original 7 specs.
Task decomposition | 10% | Strong | All 9 specs decomposed and fully implemented — 63 tasks total, every AC covered, no Coverage Gaps.
Test-first approach | 5% | Strong | Every one of the 63 Merged tasks followed the same discipline: Red tests confirmed failing for the right reason before any implementation, verified at every Gate 2 review, not retrofitted. Several self-caught test-authoring mistakes were found and fixed before treating Red as confirmed, recorded transparently.
Security & failure handling | 5% | Partial | Every one of the 63 tasks has its own Security Checklist pass, and one real production-severity gap was found and fixed mid-session (no live MongoDB connection outside tests). Still Partial, not Strong — nothing is consolidated into the standalone document Deliverable 8 asks for.
SDD traceability | 20% | Strong | Full chain intact end-to-end, now spanning 9 specs / 63 tasks: BRD -> Spec -> Gate 1 -> Plan -> Tasks -> Red -> Green -> Gate 2 -> Merge. status.md kept current same-day throughout, including honest records of self-caught mistakes and spec amendments. One hotfix followed the project's own compressed hotfix process (sdd-methodology.md #24), not an ad hoc patch.
Total

## 10-Day Timeline
Recommended 10-Day Timeline (§6)
Days 1-6 artefacts were produced in one extended session, not spread across calendar days. Actual calendar-day tracking starts fresh from here.
Day | Activity | Expected Output | Approx Effort | Status | Actual Date(s) | Notes
Day 1 | Understand requirement + Discovery | Business understanding, questions, assumptions, open decisions | 2.5-3 hrs | Done
Day 2 | BRD interpretation + SDD Spec | BRD interpretation + initial .spec.md | 3-4 hrs | Done |  | 7 specs, not 1 - broader scope than the brief anticipated.
Day 3 | Acceptance Criteria + API Contract + Test Cases | Complete specification + AC + API + spec-derived tests | 3-4 hrs | Done | 2026-09-16 | AC + API Contract + spec-derived QA test cases (7 files) all complete.
Day 4 | Gate 1 Peer Review | Review comments + revised/approved spec | 1.5-2 hrs | Done |  | All 7 specs Approved - see reviewer-identity caveat under Deliverable 9.
Day 5 | Technical Plan + Architecture | .plan.md, integration approach, data model, failure handling, ADR candidates | 3-4 hrs | Done |  | 7 plans; 1 ADR (ADR-0001, JWT auth). All Constitution Checks human-confirmed 2026-09-16.
Day 6 | Task Decomposition + AI Prompts | .tasks.md, task-to-AC mapping, implementation prompts | 2.5-3 hrs | Done | 2026-09-16 | All 7 specs done - 31 tasks, 31 per-task prompt files.
Day 7 | Test-first implementation | RED tests + first implementation increment | 4-5 hrs | Done | 2026-09-19 to 2026-09-21 | Red-first discipline held for all 63 tasks — every task's own Red confirmation recorded in status.md before its Green implementation.
Day 8 | Guided implementation | Remaining core implementation + integration | 4-5 hrs | Done | 2026-09-19 to 2026-09-21 | All 63 tasks across all 9 specs implemented and integrated. Real integration bugs found via actual usage were fixed as proper tasks: a route collision, 3 access-control carve-out gaps, a missing DB connection, missing navigation, and zero screen styling.
Day 9 | Validation + Security + Gate 2 preparation | GREEN tests, security review, traceability | 4-5 hrs | In Progress | 2026-09-19 to 2026-09-21 | 638/638 tests passing (tsc/eslint/next build all clean), Gate 2 evidence prepared and reviewed for all 63 tasks. Remaining: the standalone security review document (Deliverable 8).
Day 10 | Gate 2 + Final Presentation | Final artefact chain + demo + 10-15 min walkthrough | 2.5-3 hrs | In Progress | 2026-09-19 to 2026-09-21 | Gate 2: Done — all 63 tasks reviewed and Merged by a named human reviewer. Remaining: the final 10-15 min walkthrough/demo hasn't happened yet.

## Milestones
Milestones (§7)
4 major milestones the assessment is segregated into.
Milestone | Days | Expectation | Status | Notes
1 - Discovery & Specification | 1-2 (through Day 3) | Demonstrate no premature coding: BRD -> Spec -> AC -> API Contract -> Test Cases | Done | BRD -> Spec -> AC -> API Contract -> spec-derived Test Cases all complete for the original 7 specs.
2 - Gate 1 | Day 3 | A real peer review, not just a presentation | Done | All 9 specs Approved via @generate-gate1-review.md (7 original + 2 UI-layer specs added during implementation), plus 3 mid-implementation amended-AC re-confirmations.
3 - Plan -> Tasks | Days 4-5 | Plan complete, tasks decomposed | Done | All 9 plans Done and human-confirmed. All 9 specs' task decomposition complete — 63 tasks total (grew from an initial 31 as the 2 UI specs and real-implementation gaps were added).
4 - Implementation & Gate 2 | Days 6-8 | Task -> Prompt -> Test (RED) -> Implementation -> Test (GREEN) -> Review | Done | All 63 tasks implemented, Gate 2 reviewed, and Merged by a named human reviewer. 638/638 tests passing, tsc/eslint/next build all clean. Remaining, outside this milestone's own scope: a standalone security assessment document and a final demo/walkthrough.
Overall effort expectation: ~30-35 hours over 8 working days. See 'Effort Log' sheet.

## Effort Log
Effort Log
Log actual hours as work continues; compare against the ~30-35 hr / 8-day expectation.
Date | Day # (from §6) | Hours logged | Running total | Notes

## Next Actions
Immediate Next Actions (in order)
# | Action | Status
1 | Close Deliverable 3 / Milestone 1: run @generate-test-cases.md for <slug> for each of the 7 specs. | Done
2 | Finish Milestone 3: run @generate-tasks.md for <slug> for the remaining 5 specs. | Done
3 | Test-first implementation across all tasks (Day 7-8): 63 tasks across 9 specs, every one Red-confirmed before Green, every Green Gate-2-reviewed and Merged. | Done
4 | Draft a standalone Security Assessment document (Deliverable 8) - consolidate what's already distributed across specs/constitution.md rather than starting from scratch. | Not Started
5 | Gate 2 review (@code-review.md) — all 63 tasks reviewed and Merged. | Done
6 | Decide what to do with the stale test_cases/_integration.md. | Done
7 | Implement the drafted-but-not-yet-applied hotfix, HOTFIX-2026-0921-raw-action-labels.spec.md (.ai-context/hotfixes/) — raw system keys shown instead of human-readable text in both panels' Action History. Awaiting explicit go-ahead to implement. | Not Started
8 | Final demo / 10-15 min walkthrough (Day 10 / Milestone 4's own remaining piece) — hasn't happened yet. | Not Started