## Timeline
Day | Activity | Detailed Tasks | Expected Output | Milestone | Status | Owner | Dependencies | Notes
Day 1 | Discovery | Understand requirement, identify ambiguity, assumptions | Business understanding doc | Milestone 1
Day 2 | Specification | BRD interpretation, initial spec.md | Initial specification | Milestone 1
Day 3 | AC + API + Tests | Define acceptance criteria, API contracts, test cases | Complete spec + tests | Milestone 1
Day 4 | Gate 1 Review | Peer review and revisions | Approved spec | Milestone 2
Day 5 | Technical Plan | Architecture, data model, ADRs | plan.md | Milestone 3
Day 6 | Task Breakdown | tasks.md, AI prompts | Task mapping | Milestone 3
Day 7 | Implementation (RED) | Write failing tests, start implementation | Initial code | Milestone 4
Day 8 | Implementation | Complete core features + integration | Working modules | Milestone 4
Day 9 | Validation | Testing, security, traceability | Green tests + review | Milestone 4
Day 10 | Final Delivery | Gate 2 + presentation | Final demo | Milestone 4