## Day Tracker
SDD Assessment — Employee Internal Transfer Journey — Day-by-Day Tracker
Day | Date | Milestone | Planned Activity | Expected Output | Planned Hrs | Actual Hrs | Status
1 |  | M1: Discovery & Spec | Understand requirement + Discovery | Business understanding, questions, assumptions, open decisions | 3 |  | Not Started
2 |  | M1: Discovery & Spec | BRD interpretation + SDD Spec | BRD interpretation + initial .spec.md | 4 |  | Not Started
3 |  | M1: Discovery & Spec | Acceptance Criteria + API Contract + Test Cases | Complete specification + AC + API + spec-derived tests | 4 |  | Not Started
4 |  | M2: Gate 1 | Gate 1 Peer Review | Review comments + revised/approved spec | 2 |  | Not Started
5 |  | M3: Plan & Tasks | Technical Plan + Architecture | plan.md, integration approach, data model, failure handling, ADR candidates | 4 |  | Not Started
6 |  | M3: Plan & Tasks | Task Decomposition + AI Prompts | tasks.md, task-to-AC mapping, implementation prompts | 3 |  | Not Started
7 |  | M4: Implementation & Gate 2 | Test-first implementation | RED tests + first implementation increment | 5 |  | Not Started
8 |  | M4: Implementation & Gate 2 | Guided implementation | Remaining core implementation + integration | 5 |  | Not Started
9 |  | M4: Implementation & Gate 2 | Validation + Security + Gate 2 prep | GREEN tests, security review, traceability | 5 |  | Not Started
10 |  | M4: Implementation & Gate 2 | Gate 2 + Final Presentation | Final artefact chain + demo + walkthrough | 3 |  | Not Started
|  |  | Total |  | 38 | 0

## Task Tracker
Implementation Task Tracker (employee-internal-transfer)
Task ID | Description | Maps to AC | Owner | Planned Day | Status | Blocked By | Notes
employee-internal-transfer.T01 | Migrations: transfer_requests, transfer_request_steps | AC1, AC10 |  | 7 | Not Started
employee-internal-transfer.T02 | POST /api/transfer-requests (submit) | AC1 |  | 7 | Not Started | T01
employee-internal-transfer.T03 | GET /api/transfer-requests/{id} (status) | AC10 |  | 7 | Not Started | T01
employee-internal-transfer.T04 | Manager decision endpoint | AC2, AC3 |  | 8 | Not Started | T02
employee-internal-transfer.T05 | HR decision + conditional step rules | AC4-AC8 |  | 8 | Not Started | T04
employee-internal-transfer.T06 | Downstream callback + completion/failure logic | AC9, AC12, AC13 |  | 8 | Not Started | T05
employee-internal-transfer.T07 | Withdraw endpoint | AC11 |  | 8 | Not Started | T05
employee-internal-transfer.T08 | Frontend: submission wizard | AC1 |  | 9 | Not Started | T02
employee-internal-transfer.T09 | Frontend: status & pending-actions view | AC10 |  | 9 | Not Started | T03
employee-internal-transfer.T10 | Frontend: withdraw action | AC11 |  | 9 | Not Started | T07
employee-internal-transfer.T11 | Security/observability hardening | cross-cutting |  | 9 | Not Started | T02-T07

## Summary
Progress Summary
Metric | Value
Days Tracked | 10
Days Done | 0
Days In Progress | 0
Days Blocked | 0
Total Planned Hours | 38
Total Actual Hours | 0
Tasks Total | 11
Tasks Done | 0
Tasks In Progress | 0
Tasks Blocked | 0

## Traceability Matrix
Consolidated Traceability Matrix — BRD → AC → API → Task → Test
employee-internal-transfer ¦ single source of truth tying every artefact in .ai-context/ to every other artefact, by stable ID
BRD ID | AC ID | AC Summary | Linked Assumption(s) | API ID(s) | Spec UT ID(s) | QA Test Case ID(s) | Task ID(s) | Gate 1 Status | Gate 2 Status
BRD-001 | AC1 | Employee submits a valid transfer request | 3, 5, 8 | API01 | UT01, UT02, UT03, UT04 | UT01, UT01a, UT02, UT02a, UT03, UT03a, UT04, UT04a | T01, T02, T08 | Pending | Pending
BRD-001 | AC2 | Manager approves -> HR step opens | 1 | API04 | UT05 | UT05, UT05a | T04 | Pending | Pending
BRD-001 | AC3 | Manager rejects -> request terminates |  | API04 | UT06, UT07 | UT06, UT07 | T04 | Pending | Pending
BRD-001 | AC4 | HR approves -> conditional steps created or straight to Completed | 2, 7 | API05 | UT08 | UT08, UT08b | T05 | Pending | Pending
BRD-001 | AC5 | HR rejects -> request terminates | 2 | API05 | UT08a | UT08a | T05 | Pending | Pending
BRD-001 | AC6 | Pay-impacting change -> Payroll step | 7 | API05, API06 | UT09 | UT09 | T05, T06 | Pending | Pending
BRD-001 | AC7 | Dept/location change -> IT step | 7 | API05, API06 | UT10 | UT10, UT11a | T05, T06 | Pending | Pending
BRD-001 | AC8 | Location change -> Facilities step | 7 | API05, API06 | UT11 | UT11, UT11a | T05, T06 | Pending | Pending
BRD-001 | AC9 | Last conditional step completes -> request Completed |  | API06 | UT12 | UT12 | T06 | Pending | Pending
BRD-001 | AC10 | Employee/manager/HR view status + pending owner |  | API02 | UT13, UT14 | UT13, UT13a, UT13b, UT14, UT14a | T03, T09 | Pending | Pending
BRD-001 | AC11 | Employee withdraws before HR approval only | 4 | API03 | UT15, UT16 | UT15, UT15a, UT16 | T07, T10 | Pending | Pending
BRD-001 | AC12 | Downstream callback failure -> step Failed, not silently Completed |  | API06 | UT17 | UT17, UT17a | T06 | Pending | Pending
BRD-001 | AC13 | HR resolves a Failed step -> completion re-evaluated |  | API06 | UT18 | UT18, UT18a | T06 | Pending | Pending
Legend:
Orange fill in 'Linked Assumption(s)' = this AC depends on an open BRD-001 question (see discovery-analysis.md §5 / spec §Assumptions).
Gate 1/Gate 2 Status: set from gate-reviews/gate1-review-....md and gate2-evidence-....md as reviews happen.